## Sheet1
ID | Requirement Description | T- Shirt Size | Outcome of each task | Story points
EP-00 | Cross-Cutting AI Infrastructure
0.0.1 | Programmatic Agent Registration (Agent 1 & 2) | S | Implement Interfaces (IAgentFactory, etc.) | 16
0.0.2 | Profile & Permission Setup for Agents | S | Create specific roles for Site and Corporate agents | 16
0.0.3 | Global Instruction Base & System Rules | XS | Initial prompts and core behavior constraints | 8
EP-01 | EPIC: Agent 1 - Site Level Purchasing Assistant
FR 01 | Automatic Classification of Budget Lines
1.1.1 | Setup Vendor Activity Code master data (Table/Page) | XS | Manage activity codes (Electrical, Structure, etc.) | 8
1.1.2 | Extend Budget Line with AI classification fields | S | Add status, activity code, and confidence level fields | 16
1.1.3 | Implement AI Classification Logic (Agent SDK) | M | Logic to analyze text and propose activity codes | 32
1.1.4 | Create Classification Audit Log & Logic | S | Track and audit AI classification decisions | 16
1.1.5 | Proposed Activity Classification Review UI | S | UI for Site Manager to confirm/reject AI proposals | 16
FR 02 | Vendor Search & Project Association
1.2.1 | Extend Contact/Vendor with Activity Codes | XS | Link vendors to their specialized activities | 8
1.2.2 | AI Vendor Search Logic (Internal BC Query) | S | Find active/historical vendors by activity match | 16
1.2.3 | Supplier Search Results UI | S | Display search results with evaluation scores | 16
1.2.4 | Project Supplier Association Schema | XS | Table to link selected vendors to specific projects | 8
1.2.5 | Quick Create Supplier Form (Wizard) | S | Fast onboarding of new vendor contacts via AI | 16
FR 03 | Price Comparative Generation
1.3.1 | Price Comparative Schema (Header, Line, Supplier) | M | Core structure for comparing multi-vendor quotes | 32
1.3.2 | Integration with Project Schedule for anticipation | S | Logic to trigger comparatives 2-3 months early | 16
1.3.3 | Comparative Generation Wizard | S | UI to group budget lines by activity into comparatives | 16
1.3.4 | Price Comparative Card & List Management | M | Full management UI for comparative lifecycle | 32
FR 04 | Automated Price Requests (Email Integration)
1.4.1 | Email Template & Attachment Management | S | Templates with variables {PROJECT}, {SUPPLIER} | 16
1.4.2 | Automated Request Sending Logic | S | AI-driven email dispatch with technical specs | 16
1.4.3 | Price Request Log & Response Monitoring | S | Track sent requests and capture vendor responses | 16
FR 05 | Validation & Contract Generation
1.5.1 | Comparative Data Validation Engine | S | AI check for missing prices, terms, or retentions | 16
1.5.2 | Validation Results UI & Error Handling | S | Display warnings/errors to the site manager | 16
1.5.3 | Contract Generation Logic (Convert to PO) | M | Auto-create Purchase Header/Lines from selection | 32
1.5.4 | Contract Template & Audit Log | S | Standardize legal clauses and audit creation | 16
FR 06 | Selection Meeting & Negotiation Management
1.6.1 | Selection Meeting Scheduling & Cues | S | Integration of Meeting Date with BC Role Center cues and calendar reminders | 16
1.6.2 | AI Pre-Meeting Readiness Auditor | S | Proactive alerts identifying missing prices or terms specifically required for the selection meeting | 16
1.6.3 | Shortlist/Pre-selection Logic | XS | Action to flag "Shortlisted" suppliers for second-round consideration | 8
1.6.4 | L - Second Round Negotiation Workflow (Breakdown) |  | Automated facilitation of secondary quote rounds
1.6.4.a | Price Versioning Logic | S | Capability to store original quotes while inviting updated "Best and Final" offers | 16
1.6.4.b | Round 2 Request Automation | S | Automated dispatch of negotiation emails to pre-selected vendors with target price points | 16
1.6.4.c | Negotiation Monitoring UI | S | Dedicated view to track responsiveness and improvements in the second round | 16
1.6.4.d | Final Decision Finalization | S | Logic to lock final negotiation results and proceed to the selection outcome | 16
EP-02 | EPIC: Agent 2 - Corporate Purchasing Supervisor
FR 01 | Multi-Site Data Aggregation & Integration
2.1.1 | Consolidated Purchasing Data Schema | M | Tables to aggregate comparatives and decisions from all sites | 32
2.1.2 | Data Sync Logic between Agent 1 and Agent 2 | S | Ensure consistent data flow from site level to corporate level | 16
2.1.3 | Corporate Purchasing Policy Master Data | S | Define global rules, price limits, and approved supplier lists | 16
FR 02 | Global Purchasing Monitoring Dashboard
2.2.1 | L - Multi-Site Comparative Status View (Breakdown) |  | Consolidated monitoring dashboard for Directors
2.2.1.a | Cross-project comparative list UI | S | View status of all open comparatives across the organization | 16
2.2.1.b | Drill-down logic to Site-Level details | S | Navigation from corporate summary to specific site budget lines | 16
2.2.1.c | Visualization of purchasing funnel | S | Charts showing Request -> Received -> Selected -> Contracted | 16
2.2.1.d | Real-time data refresh and filtering | S | Filter by Project, Region, or Construction Manager | 16
FR 03 | Compliance & Policy Validation Engine
2.3.1 | L - Automated Policy Deviation Engine (Breakdown) |  | Validation engine for selection criteria & policies
2.3.1.a | Validation logic for selection criteria | S | Check if the cheapest or best-evaluated vendor was chosen | 16
2.3.1.b | Policy consistency check | S | Validate against corporate payment terms and retentions | 16
2.3.1.c | Exception management workflow | S | Allow site managers to justify deviations for Director review | 16
2.3.1.d | Deviation Alerting system | S | Automated notifications when a purchase violates a policy | 16
FR 04 | Site Manager Performance Analytics
2.4.1 | Performance Metric Calculation Engine | M | Logic to track timing, cost saving, and process compliance | 32
2.4.2 | Site Manager Performance Reporting UI | S | Visual report for Directors to compare manager efficiency | 16
2.4.3 | Automated "Recommendations for Improvement" AI | S | Agent-generated advice based on manager performance history | 16
FR 05 | Supplier Risk & Corporate Performance
2.5.1 | XL - Corporate Supplier Risk Analyzer (Breakdown) |  | High-level analysis of global supplier performance
2.5.1.a | Historical performance aggregation | M | Consolidate evaluations from multiple sites for single vendors | 32
2.5.1.b | Risk Identification Algorithm | M | AI detection of underperforming or financially risky suppliers | 32
2.5.1.c | Global Capacity Warning System | M | Alert if a vendor is over-contracted across multiple sites | 32
2.5.1.d | Corporate Supplier Recommendations | M | Suggest shifting volume to high-performing vendors | 32
FR 06 | Analytics & BI Integration
2.6.1 | External Analytics Data Export (OData/API) | S | Expose consolidated agent data for Power BI consumption | 16
2.6.2 | Corporate Level Executive Summaries | S | Narrative reports for General Management overview | 16
|  | Total story points |  | 936

## claude
ID | Requirement Description | T-Shirt Size | Story Points | Outcome
FOUNDATION
F-01 | Data Foundation — Agent 1 New Tables: Create Vendor Activity Code extensions (Keywords field), Classification Audit Log, Project Supplier Association, Supplier Search Log tables with full field definitions, keys, and relations | S | 16 | New tables deployed, accessible via BC pages
F-02 | Budget Line Table Extensions: Add AI classification fields to existing Budget Line equivalent (Proposed Vendor Activity Code, Confidence Level, Confirmation Status, Actual Vendor Activity Code, Classification Date, Classification User) | S | 16 | Budget Lines carry AI classification metadata
F-03 | Comparative & Scheduling Tables: Create Project Schedule, Price Comparative, Price Comparative Line, Price Comparative Supplier, Comparative Generation Log new tables — builds on but does not replace existing QBU Comparative Quote tables | M | 32 | Full comparative lifecycle tables available
F-04 | Email & Contract Tables: Create Email Template, Email Template Attachment, Price Request Log, Contract Template, Contract Generation Log new tables | S | 16 | Template and log infrastructure ready
F-05 | Agent 2 Analytics Tables: Create Cycle Time Analysis, Cycle Time Detail, Monitoring Alert, Monitoring Log, Vendor Evaluation, Supplier Selection Analysis, Recommendation Log new tables | M | 32 | Analytics data model for corporate supervisor agent
AGENT 1 — CLASSIFICATION
A1-01 | AI Classification Engine Codeunit: Text-analysis codeunit that reads Budget Line descriptions, matches against Activity Code keywords, assigns confidence levels (High/Medium/Low) using pattern matching + Azure OpenAI call via BC Copilot framework | L | 64 | AI proposes activity codes with confidence; extensible for ML
A1-01a | Sub-task: Keyword extraction & pre-screening (pure AL, no AI call) | S | 16 | Rule-based pre-filter reduces AI token cost
A1-01b | Sub-task: Azure OpenAI integration via BC AI codeunits for ambiguous classifications | M | 32 | AI classifies ambiguous descompuestos
A1-01c | Sub-task: Confidence scoring logic + audit log writing | S | 16 | Each classification traceable
A1-02 | Proposed Activity Classification List Page: New list page showing pending Budget Lines with AI proposals, dynamic field visibility (Actual Activity Code shown only on Reject), color coding by confidence, Save/Cancel/Show Details actions | S | 16 | Site manager can review + validate classifications
A1-03 | Business Rules & Validation Codeunit (Classification): Enforce RN-CLASS-001 to RN-CLASS-005 — status transitions, mandatory code before save, audit registration, error messages | XS | 8 | Classification business rules enforced
AGENT 1 — SUPPLIER SEARCH
A1-04 | Supplier Search Engine: Codeunit performing 3-query search (active vendors, historical vendors from Purchase Headers, contact suggestions) + result categorization + Project Supplier Association creation + Supplier Search Log | S | 16 | Suppliers categorized and associated to project
A1-05 | Find Suppliers Dialog + Supplier Search Results List: Multi-select activity code dialog + results page with 3 FastTabs (Active/Historical/Suggested), Include checkboxes, Quick Create Supplier form (name, email, activity code) | M | 32 | Site manager searches and creates supplier contacts from BC
AGENT 1 — COMPARATIVE GENERATION
A1-06 | Comparative Generation Engine: Codeunit that reads Project Schedule dates, calculates anticipation (default 60 days), filters classified budget lines, groups by activity code, creates Price Comparative + Lines + Supplier records, sets Meeting Date (Execution Date −30 days) | M | 32 | Comparatives auto-generated with correct scheduling
A1-07 | Generate Comparatives Dialog + Confirmation Page: Configuration dialog (Advance Days, Include Only Verified, Group by Activity) + confirmation page showing comparatives to be created + Comparative Card page (GeneralInfo, Lines, Suppliers FastTabs, actions) | M | 32 | Full UI for comparative creation and editing
AGENT 1 — PRICE REQUEST
A1-08 | Email Send Engine Codeunit: Template resolution by activity code, variable replacement ({SUPPLIER_NAME}, {PROJECT_NAME}, {DEADLINE}, etc.), attachment management, BC email dispatch, Price Request Log registration | M | 32 | Emails sent to suppliers with correct templates
A1-09 | Send Price Request Dialog + Price Request Log List: Dialog showing supplier count, template preview, attachment upload; log list showing Days Since Request calculation | S | 16 | Site manager sends and monitors price requests
AGENT 1 — VALIDATION
A1-10 | Comparative Validation Engine: 5-phase validation codeunit (price received, payment terms, retentions, quantity/unit consistency, overall completeness), severity classification (Error/Warning/Info), Validation Result + Issue records creation | M | 32 | All data quality issues surfaced automatically
A1-11 | Validation Results Page: Card page showing summary (critical errors, warnings, info counts), issues repeater with Fix/Ignore actions, Validate Again button, comparative status update to "Ready for Selection" | S | 16 | Site manager corrects issues inline
AGENT 1 — CONTRACT GENERATION
A1-12 | Contract Generation Engine: Codeunit bridging from selected Price Comparative Supplier → BC Purchase Header creation with all copied fields (vendor, payment terms, retention, project, comparative reference) + Purchase Lines per budget line, unit cost calculation | M | 32 | Purchase Orders auto-created from comparatives
A1-13 | Generate Contract Dialog + Confirmation Page + Purchase Header Extensions: Contract template selection dialog; confirmation page listing generated contracts; table extensions on Purchase Header/Line for Comparative No., Execution Guarantee Retention %, Contract Template Used, Budget Line No., Work Unit Code | S | 16 | Contracts reviewable before confirmation
AGENT 1 — MEETING REMINDERS & ALERTS
A1-14 | Meeting Reminder & Alert Codeunit: Scheduled job checking Meeting Date − Reminder Days = Today condition, dispatching BC notifications to role center, alert for pending classification/comparative actions | XS | 8 | Proactive reminders prevent missed deadlines
AGENT 1 — AL AGENT DEFINITION
A1-15 | Agent 1 AL Registration: enumextension for Agent Metadata Provider, IAgentFactory codeunit (Copilot capability registration, install codeunit), IAgentMetadata codeunit (display name, profile assignment), IAgentTaskExecution codeunit | S | 16 | Agent 1 registered and activatable in BC
A1-16 | Agent 1 Custom Profile + Page Customizations: New profile QB-AGENT-OBRA, page customizations for all agent-facing pages (ClearActions, ClearLayout, ClearViews, DeleteAllowed=false, only relevant fields visible) | XS | 8 | Agent has minimal, precise UI surface
A1-17 | Agent 1 Permission Set: Custom permission set covering exact table/page/codeunit access needed — read on Budget Lines, Vendors, Jobs; insert/modify on Classification, Comparative, Price Request tables; no delete on financial documents | XS | 8 | Least-privilege security for Agent 1
A1-18 | Agent 1 English Instructions + Task Definitions: Structured natural language instructions (Responsibilities, Guidelines, step-by-step Instructions sections per BC toolkit pattern), task definitions for: Classify Descompuestos, Find Suppliers, Generate Comparatives, Send Price Requests, Validate Comparative, Generate Contract | M | 32 | Agent executes workflows correctly via LLM guidance
AGENT 2 — CYCLE TIME MONITORING
A2-01 | Cycle Time Analysis Engine: 4-step codeunit — historical data collection from Price Request Log, mean/std-dev/percentile calculation, active cycle analysis, deviation detection with severity scoring (Medium/High/Critical) | L | 64 | Corporate agent detects delays across all projects
A2-01a | Sub-task: Historical data aggregation & statistics calculation (avg, std dev, P75, P90) | M | 32 | Statistical foundation for benchmarking
A2-01b | Sub-task: Active cycle deviation detection & Monitoring Alert record creation | M | 32 | Real-time delay alerts generated
A2-02 | Purchasing Monitoring Dashboard: Multi-FastTab page (filters, summary KPIs, cycle grid with deviations, active alerts grid with Acknowledge/Send Notification actions, Generate Report/Export to Excel buttons) | M | 32 | Corporate view of all purchasing cycles
A2-03 | Cycle Time Analysis Page: Detailed drill-down page showing completed/in-progress cycles, mean times by phase, statistical summaries | S | 16 | Detailed cycle time data accessible
AGENT 2 — SUPPLIER SELECTION ASSISTANCE
A2-04 | Weighted Scoring Engine: 5-step codeunit — historical data aggregation (contracts, delivery rates, quality rates), capacity analysis vs. historical max volume, contractor concentration pattern detection, weighted score calculation (eval 40% + timeliness 30% + quality 20% + distance 10%), top-3 ranking | L | 64 | Evidence-based supplier recommendation generated
A2-04a | Sub-task: Historical metrics calculation from Purchase Headers + Vendor Evaluations | M | 32 | Metrics foundation for scoring
A2-04b | Sub-task: Weighted scoring formula + capacity risk rules + concentration pattern detection | M | 32 | Scoring and risk assessment
A2-05 | Supplier Selection Analysis Page: Displays providers ranked by weighted score with capacity risk indicators, concentration alerts, recommendation highlighted, Accept/Select Other actions | M | 32 | Corporate director acts on AI recommendations
A2-06 | Vendor Evaluation Form + Manual Scoring: Page for manual vendor evaluation entry (quality, timeliness, communication, price competitiveness scores 0-5), auto-calculate Overall Score, link to contract | S | 16 | Evaluation data entered after contract completion
A2-07 | Supplier Evaluation Dashboard: List page with search/filter, color-coded Weighted Score column, multi-export options, drill-down to details and reports | S | 16 | Corporate-level vendor performance visibility
AGENT 2 — AL AGENT DEFINITION
A2-08 | Agent 2 AL Registration: enumextension, IAgentFactory, IAgentMetadata, IAgentTaskExecution codeunits for Agent 2 (Corporate Supervisor) | S | 16 | Agent 2 registered and activatable
A2-09 | Agent 2 Custom Profile + Page Customizations: Profile QB-AGENT-CORP with access to Monitoring Dashboard, Supplier Selection pages, cross-project comparative lists | XS | 8 | Agent 2 has correct corporate-level UI surface
A2-10 | Agent 2 Permission Set: Read-access to all comparative data, write access to Monitoring Alerts/Logs, Recommendation Log, no access to individual project financial data beyond comparatives | XS | 8 | Least-privilege for corporate supervisor
A2-11 | Agent 2 English Instructions + Task Definitions: Instructions for: Monitor Cycle Times, Generate Deviation Alerts, Assist Supplier Selection, Detect Concentration Risks | M | 32 | Agent 2 executes corporate oversight workflows
CROSS-CUTTING
X-01 | Integration Testing — Agent 1 End-to-End: Test flows: Classification → Supplier Search → Comparative Generation → Price Request → Validation → Contract Generation. Agent task playground validation in sandbox | M | 32 | Agent 1 full workflow verified
X-02 | Integration Testing — Agent 2 End-to-End: Test flows: Cycle monitoring → Alert generation → Supplier Selection → Recommendation acceptance | S | 16 | Agent 2 full workflow verified
X-03 | Documentation & Deployment Guide: Agent configuration guide, permission setup runbook, profile assignment instructions, instruction update procedure | S | 16 | Operations team can maintain and update agents
ID | Requirement Description | T-Shirt Size | Story Points | Outcome
MVP-F-01 | Core Data Tables: Create Vendor Activity Code (Keywords extension), Classification Audit Log, Project Supplier Association tables — minimum viable data foundation | XS | 8 | Activity code-vendor-project data model ready
MVP-F-02 | Budget Line Extensions: Add AI classification fields to Budget Lines (Proposed Vendor Activity Code, Confidence Level, Confirmation Status, Classification Date/User, Status option) | XS | 8 | Budget lines carry classification metadata
MVP-F-03 | Price Comparative Core Tables: Price Comparative header + Price Comparative Line + Price Comparative Supplier — minimal comparative structure (reuses existing QBU Comparative Quote concepts but adds AI scheduling fields) | S | 16 | Core comparative tables support the agent workflow
MVP-A1-01 | AI Classification Engine — Keyword-Based (MVP): Rule-based AL codeunit matching Budget Line description text against Activity Code Keywords field; assigns confidence (High=exact match, Medium=partial, Low=fallback); writes Classification Audit Log; no Azure OpenAI call in MVP | S | 16 | Agent proposes activity codes — validated manually
MVP-A1-02 | Proposed Activity Classification List Page: New list page with AI proposals, color-coded confidence (Green/Yellow/Red), Confirmation Status dropdown (Confirmed/Rejected/Pending), conditional Actual Activity Code field, Save Classifications action with validation | S | 16 | Site manager reviews and approves classifications
MVP-A1-03 | Supplier Search (Simplified): Single-query search finding active vendors matching Activity Code; displays results in simple list; creates Project Supplier Association on selection; logs search in Supplier Search Log | XS | 8 | Suppliers linked to projects by activity code
MVP-A1-04 | Comparative Generation (Core): Generate Comparatives Dialog (Advance Days, Group by Activity Code options) + engine codeunit that identifies classified budget lines with upcoming execution dates, creates Price Comparative records + Lines + Supplier links from Project Supplier Association | S | 16 | Comparatives auto-generated with correct anticipation
MVP-A1-05 | Agent 1 AL Registration + Copilot Capability: enumextension on Agent Metadata Provider, IAgentFactory with Copilot capability registration, install codeunit, IAgentMetadata codeunit | XS | 8 | Agent 1 appears in BC Agent list and can be activated
MVP-A1-06 | Agent 1 Custom Profile + Permission Set: Profile QB-AGENT-OBRA-MVP with page customizations (minimal fields exposed); Permission set with least-privilege access to classification, comparative, vendor, budget tables | XS | 8 | Agent runs securely with correct UI surface
MVP-A1-07 | Agent 1 Task Execution + English Instructions: IAgentTaskExecution codeunit wiring tasks to existing pages; structured English instructions (Responsibilities/Guidelines/Instructions) for 3 core tasks: Classify Descompuestos, Find Suppliers by Activity, Generate Price Comparatives | S | 16 | Agent autonomously executes 3 core tasks
TOTAL MVP | 10 items |  | 120